## Sheet1
Activities | Task | Department / Team | Task Owner | Approved By | Team Members | Start Date | End Date | Start Time | End Time | Target | Count / Person / Day | Available Resources | TBH | Budget | Milestone Target | Milestone Achieved | Output Target | Current Status of Output Target | Comments
Product Development-Swifterz Platform | Planning Meet | Tech | Jayamani/Meena | Ram | Saranya | 2024-04-13 | 2024-04-13 | 22/04/2024
Product Development-Swifterz Platform | Requirements Gathering | Tech | Jayamani/Meena | Ram | Saranya | 2024-04-15 | 2024-04-15
Product Development-Swifterz Platform | Product Research | Tech | Jayamani/Meena | Jayamani/Meena | Saranya | 2024-04-16 | 2024-04-16
Product Development-Swifterz Platform | Content Preparation | Tech | DM | Jayamani/Meena | DM | 2024-04-16 | 2024-04-18
Product Development-Swifterz Platform | Design Preparation | Tech | DM | Jayamani/Meena | DM/ Aswin | 2024-04-16 | 2024-04-17
Product Development-Swifterz Platform | Review to start Project | Tech | Jayamani/Meena | Jayamani/Meena | Saranya/Aijth/Aswin | 2024-04-17 | 2024-04-17
Product Development-Swifterz Platform | Architecture Design | Tech | Jayamani/Meena | Jayamani/Meena | Saranya/Aswin | 2024-04-17 | 2024-04-17
Product Development-Swifterz Platform | Review | Tech | Jayamani/Meena | Jayamani/Meena | Saranya/Aijth/Aswin | 2024-04-17 | 2024-04-17
Product Development-Swifterz Platform | Prototyping | Tech | Jayamani/Meena | Jayamani/Meena | Saranya | 2024-04-17 | 2024-04-17
Product Development-Swifterz Platform | Review | Tech | Jayamani/Meena | Jayamani/Meena | Saranya | 2024-04-17 | 2024-04-22
Product Development-Swifterz Platform | Development | Tech | Jayamani/Meena | Ram /Jayamani/Meena | Saranya/ Aijith | 2024-04-17 | 2024-04-25
Product Development-Swifterz Platform | Review | Tech | Jayamani/Meena | Ram /Jayamani/Meena | Saranya/ Aijith | 2024-04-17 | 2024-04-22
Product Development-Swifterz Platform | Testing | Tech | Jayamani/Ram | Ram | Meena | 2024-04-17 | 2024-04-25
Product Development-Swifterz Platform | Review | Tech | Jayamani/Meena | Ram /Jayamani/Meena | Meena | 2024-04-23 | 2024-04-25
Product Development-MINE Platform | Planning Meet | Tech | Jayamani/Meena | Ram /Jayamani/Meena | Turab Hussain | 2024-04-13 | 2024-04-13
Product Development-MINE Platform | Requirements Gathering | Tech | Jayamani/Meena | Ram /Jayamani/Meena | Turab Hussain | 2024-04-15 | 2024-04-15
Product Development-MINE Platform | Product Research | Tech | Jayamani/Meena | Jayamani/Meena | Turab Hussain | 2024-04-16 | 2024-04-16
Product Development-MINE Platform | Content Preparation | Tech | DM | Jayamani/Meena | DM | 2024-04-16 | 2024-04-18
Product Development-MINE Platform | Design Preparation | Tech | DM | Jayamani/Meena | DM/ Aswin | 2024-04-16 | 2024-04-17
Product Development-MINE Platform | Review to start Project | Tech | Jayamani/Meena | Jayamani/Meena | Turab Hussain/Aswin | 2024-04-17 | 2024-04-17
Product Development-MINE Platform | Architecture Design | Tech | Jayamani/Meena | Jayamani/Meena | Turab Hussain/Aswin | 2024-04-17 | 2024-04-17
Product Development-MINE Platform | Review | Tech | Jayamani/Meena | Jayamani/Meena | Saranya/Aijth/Aswin | 2024-04-17 | 2024-04-17
Product Development-MINE Platform | Prototyping | Tech | Jayamani/Meena | Jayamani/Meena | Turab Hussain | 2024-04-17 | 2024-04-17
Product Development-MINE Platform | Review | Tech | Jayamani/Meena | Jayamani/Meena | Turab Hussain | 2024-04-17 | 2024-04-22
Product Development-MINE Platform | Development | Tech | Jayamani/Meena | Ram /Jayamani/Meena | Turab Hussain | 2024-04-17 | 2024-04-25
Product Development-MINE Platform | Review | Tech | Jayamani/Meena | Ram /Jayamani/Meena | Turab Hussain | 2024-04-17 | 2024-04-22
Product Development-MINE Platform | Review | Tech | Jayamani/Meena | Ram /Jayamani/Meena | Meena | 2024-04-23 | 2024-04-25
Product Development-MINE Platform | Testing | Tech | Jayamani/Meena | Ram /Jayamani/Meena
Product Development-MINE Platform | Review | Tech | Jayamani/Meena | Ram /Jayamani/Meena
Product Development-AECearth Hub
Product Development-AECearth Acedmeny